## Sheet1
Responsible
Accountable
Consulted
Informed
| Project Tasks | Project Manager | Project Sponsor | Project supervisor | Chief Aeronautical Engineer | Architect and designer | Quality conformance analyst | Environmental Experts
1 | Selection of Project Teams (3 months)
1.1 | Project Manager Selection
1.1.1 | Project Supervisor Selection
1.2 | Hire designer and architect
1.2.1 | Hiring of construction engineers and teams
1.3 | Hire chief aeronautical engineer
1.4 | Select quality conformance analyst
1.5 | Hire tech team
1.6 | Create project charter
1.7 | Approval of project charter by sponsors
2 | Land Selection
2.1 | Define land requirements
2.2 | Shortlist possible locations
2.2.1 | Inspect site environment
2.2.2 | Inspect the fitness of land for runways
2.3 | Finalizing the Project Site
2.4 | Approval for construction on selected sites.
3 | Construction Planning
3.1 | Advanced Study of Possible Environmental Impact
3.2 | Consultation from the Meteorological Engineers
3.3 | Create the Concept Map for the Airport
3.3.1 | Create Design and Blueprints
3.3.2 | Create Prototype
3.4 | Approval of Sponsor for the Prototype
3.4.1 | Revising the Prototype and Approving Changes
3.5 | Finalizing the Design
3.6 | Clearance of Safety, Security and Capacity
3.6.1 | Clearance for Airport Access System
3.7 | Technical Approvals
3.1.1 | Environmental Impacts Analysis Approvals
3.8 | Confirmation of Project Member’s Roles
3.9 | Create Required Raw Material’s List
3.1 | Finalizing Suppliers for Raw Materials
3.11 | Contracts for Labors
4 | Construction
4.1 | Site Clearance
4.2 | Procurement of Raw Materials
4.1.1 | Land Allocation for Individual Entity
4.2 | Creation of Foundation for the Airstrip
4.3 | Laying out the Airstrip.
4.3.1 | Markings of Airstrip
4.3.2 | Following Lights and other Lighting System
4.4 | Elevation of the Platform for the Terminal
4.4.1 | Construction of the Terminal Structure
4.4.2 | Interior Designing of the Terminal
4.5 | Construction of Hanger and Maintenance facility
4.6 | Air Traffic Control Construction
4.7 | Construction of Airport Wind Observation system
4.8 | Installation of Automatic Landing System
4.9 | Installation of Safety Mechanism (Fire Evacuation Services and Emergency exits)
5 | Testing
5.1 | Testing of Airstrip using Simulations
5.2 | Testing of all the Equipments Pertaining to Runway
5.3 | Test Run of Flight
5.4 | Testing of the Automatic Landing System
5.5 | Fixing Loopholes and Final Touches
5.6 | Compliance of Requirements for the Terminal as per Stakeholders.